## 2024 Actions
Disability Action Plan 2024
From the Victorian State Government guide to Disability Action Plans: | Reducing barriers to persons with a disability accessing goods, services and facilities | Reducing barriers to persons with a disability obtaining and maintaining employment | Promote inclusion and participation in the community of persons with a disability | Achieve tangible changes in attitudes and practices which discriminate against persons with a disability |  | % Outcomes achieved
Council 2024 actions: |  |  |  |  | Indicators of achievement: | Q1 | Q2 | Q3 | Q4 | Comments:
Promote Sunraysia, with the aim of addressing the thin market of allied health and other disability support providers | X | [6 empty] | 75% | 100% | Information shared with DAN Members via Yammer Site- Accessible Tourism Video shared Ongoing sharing at DAN Meetings
Review disability awareness training for all Council staff, and provide this training, to ensure Council is responsive and listening to customers and residents with disability |  |  |  | X |  | 85% |  |  |  | Disability Awareness training offered to staff January 2023 and new training developed will undertake after June 2023 - CDC Buslines Disability Training Undertaken Aug 2023 - Good response CDC Planned Training in conjunction with wellbeing team - not completed as yet will be in 2024 Held over till After June 2024
Work with local sporting clubs and organisations on disability awareness, to promote inclusion of people with disability in sports |  |  | X |  |  |  |  | 75% |  | Share information with groups about sport for people with disability and partner with Mallee Sports Assembly Currently looking at a Wheelchair Basketball and working with local groups to develop
Work with Council's Human Resources department to ensure recruitment processes are accessible for candidates with disability; possible workshop for Disability Employment Services providers on how to best support candidates that may be applying for roles at Council. |  | X | [5 empty] | 25% |  | Disability Awareness Training development will assist with this in 2024
Refresh access map, including updated recharge points etc | X |  |  |  |  | 75% | 85% | 95% |  | Undertake mapping with Visitor Information Website for accessability commencing August 2023 - Mapping underway for all Disability parking, Toilets, Changing Places Mapping underway Sept 2023 but not completed yet. Mapping completed and on VIsit Mildura website December 2023. Plan to add to Council website in January 2024 and run some media regarding the mapping info. Mapping completed Feb 2024 and awaiting Marketing
Ouyen "Become Connected" Expo in Feb 2023? | X |  | X |  |  |  |  | 100% |  | Holding a Ouyen Health Day June 2024 and Seniors Day in July 2024
Accessibility - MLAK snap send solve, parking across footpaths, clear pathways for gophers | X |  | X |  |  |  |  | 50% |  | Information developed and to be distributed at Council events also Changing Places Information shared and the changing places included in the mapping. Also invitation to DAAC Committee to attend Carer Expo March 2024. Utilise Snap Send Solve when dealing with customers
Helping hospital to understand disability and discussion about sensory room at hospital Invite Hosp to attend DAAC Meeting March 2022 - invitation sent on 2 occasions | X |  |  | X |  | 75% |  | 100% |  | Jeni has met with hospital andoffered for attendance at DAAC meeting.. Have also met with Disability Officer from Bendigo Health who is working with hospital. No further action with hospital. Hospital person attended February 2024 DAAC meeting. Invitation to DIAC Members to be on hospital committee - June 2024
Sensory Rooms | X |  | X |  |  | 85% |  |  |  | Jeni has met with hospital and will arrange hospital to attend DAAC March meeting, gave fiddle toys to hospital admin for use with patients, Discussion with Intereach to have a sensory tent available for hire and plan to utilise powerhouse basement for quiet space for events
Wider transport issues, buses, trains and planes | X |  | X |  |  | 85% |  |  |  | Buses in Mildura and difficulties for people with vision difficulties and all people with disabilities - Jeni met with buslines and undertook Disability aawareness training August 2023' Meet with VLine and VicROads Planning regarding various items. Discussion with PTV and VIcTrack in regards to problems with Trains and tracks and also Buses for Ouyen
Mallee Track cannot access ??? The bus etc and transport | X |  |  |  |  | 80% |  |  |  | Jeni has made contact with Swan Hill bus lines and require a plan to be sent to Public Transport Victoria - Contact Emma 50324677 emmap@busbiz.net.au. Discussion at Ouyen Neighbourhood house held in December 2022. Have also put in a complaint via Claire Galvin to Public Transport Victoria and awaiting a reply - No progress recontacted Oct 2023
Development of a communication plan for people with a disability. | X |  | X |  |  | 75% |  |  |  | Discussion with Jill regarding Braille for signage at Rio Vista Park
Scooter Forum | X |  |  | X |  | 10% |  | 100% |  | Nicole Cavallaro has arranged Scooter Forum in March in Ouyen and Mildura
Access at a Glance Project with Intereach | X |  |  | X |  | 90% |  |  |  | DAAC Committee to participate, project about to commence April 2023 - 10 Businesses documented August 2023. Plan to launch in Jan/Feb 2024 DAAC Members attended media call Dec 2023 with Mildura Mayor INT- 20243649
Carer Project Mallee Track with Bendigo Health | X |  |  | X |  | 75% |  | 100% |  | Planning underway - just working on when will commence. First carer event is Mallee Track 25 Oct 2023, second event held Dec 2023 and plans for Feb 2024 - Event Held March 2024 & Coffee with a Cop 24/3/2024 alo other events in June 2024
DAAC Committee profile to be actively promoted through any Council events | X |  |  | X |  | 25% |  | 75% |  | Ongoing to be shared with any Council events - Carers Expo
DAAC Annual Plan Information for Council Plan - July 2023-June 2024 | X |  | X | X |  | 100% |  | 100% |  | INT-202321761 - 2023 and INT - 2024931 for 2024
Etiwanda Wetlands Accessibility | X |  |  | X |  | 95% |  |  |  | Project commencing April 2023. Equipment ordered and awaiting supply - refer Susan
Pedestrian Crossing 15th/Deakin near Aldi | X |  |  | X | 100% |  |  |  |  | Meet with VicROads REF ETS 502894940 Letter requests sent Physiotherapists and SRS Information Only
Pedestrian Crossing 11th near Langtree parade | X |  |  | X | 100% |  |  |  |  | Meet with Vicroads REF 502912243 Letter request sent from Dept of Educ as well Information Only
Work with local Community groups to share information and online workshops for Children with Disabilities | X |  | X |  |  | 25% |  | 85% |  | Share via email any workshops or information suitable for people with disabilities
Additional Items for DAAC Committee
[9 empty] | 88% | 18 Items March 2024
[9 empty] | 90% | 18 Items June 2024

## Media
Media 2024
2024-03-30
6 March 2024 Sunraysia Daily
Mapping - February 2024 | For Council MRCC Website and also VisitMildura Website
28 February 2024 - Newspaper advertising
2024-05-01
Hi Jeni
We want to say a big “Thank You” for your support in sharing information about our Advocating at School workshop with your network.
It was a great success and with your help, we reached capacity in all the sessions. We met parents looking to improve their child's learning outcomes and gain greater support. They now have information that helps them feel more confident to advocate for their child at school.
We received feedback from attendees that shows 98% of the information was easy to understand and 91% indicated they have a better understanding of Individual Education Plans (IEP).
Feedback like this highlights a need to provide families with accurate and clear information.
“It was so comprehensive and the personal experiences from the facilitators made it much more relatable. With this information, I feel empowered to advocate for my son at school.” Parent
Once again, thank you for your support and l Iook forward to sharing more workshops with your network in the future.
Warm regards,
Sophie Shield
Marketing and Communications Officer
T 03 9880 7055 or 1800 654 013 (regional callers)
W https://acd.org.au Follow us @acdvic Unsubscribe